## Slide 1: WES Project Plan
Phase 1: Migration | Phase 2: Integration (Post Go-Live)
Apr 13 – Jul 3, 2026 | 60 Working Days
⚠ DISCLAIMER: This timeline is tentative and subject to change. Dates may shift based on scope changes, API/credential availability from WES, content transformation complexity, defect resolution timelines, resource availability (WES or Knowmax), or external integration dependencies. Commercials may also change based on final scope.

## Slide 2: Overview & How to Read the WBS
This WBS breaks down the WES Project Plan into a structured, trackable format across 2 phases, 6 sprints, and 60 working days (Apr 13 – Jul 3, 2026). Every task, deliverable, client obligation, milestone, risk, and assumption from the source project plan is captured.
Column | Purpose
WBS # | Hierarchical numbering. Suffixes: KD, WR, D, M, A, R
Phase | Phase 1 (Migration) and Phase 2 (Integration Post Go-Live)
Sprint | Sprint grouping with week range
Type | Task, Summary, Milestone, Knowmax Deliverable, Deliverable, WES Requirement, Assumption, or Risk
Task/Deliverable | Description of the work item
Owner | WES, Knowmax, WES / Knowmax, or Knowmax / WES
Start/End Date | Working-day dates (Mon–Fri only)
Duration | NETWORKDAYS formula – working days only
Status | Not Started, In Progress, Completed, On Hold, Blocked
Dependencies | WBS # of prerequisite items
Notes | Assumptions, conditions, context

## Slide 3: Row Types & Color Coding
Summary
Sprint-level summary row showing total date range and duration
Task
Executable work items performed by Knowmax, WES, or both
◆ Milestone
Checkpoint/gate with zero duration – go/no-go before next sprint
Knowmax Deliverable
Artifact Knowmax must provide to WES (e.g., SSO setup, Platform, UAT plan )
Deliverable
Output WES produces (e.g., SSO setup, UAT plan)
WES Requirement
Action WES must take (e.g., conduct UAT, provide APIs, review content, provide feedback)
Assumption
Stated assumption the plan depends on
Risk
Identified risk to monitor and escalate

## Slide 4: Sprint Timeline
Sprint | Weeks | Dates | Days | Focus
Sprint 0 | Wk 0–2 | Apr 13 – Apr 24 | 10 | Prep: kickoff, governance, APIs, environments
Sprint 1 | Wk 3 | Apr 27 – May 1 | 5 | Initial Migration: SSO, migration script, endpoint validation
Sprint 2 | Wk 4 | May 4 – May 8 | 5 | Full Migration: UAT migration, content transformation, data integrity
Sprint 3 | Wk 5–6 | May 11 – May 22 | 10 | SIT & KUT: system integration testing, key user training, UAT
Sprint 4 | Wk 7–8 | May 25 – Jun 5 | 10 | Final Validation: UAT with users, defect resolution, go-live
Sprint 5 | Wk 9–12 | Jun 8 – Jul 3 | 20 | Phase 2 Integration: post go-live workflows, testing, deployment

## Slide 5: Key Milestones
WBS # | Milestone | Date | Detail
1.1.M1 | Prep Phase Complete | Apr 24, 2026 | Project plan finalized, environments ready. Gate to Sprint 1.
1.2.M1 | Initial Migration Complete | May 1, 2026 | SSO set up, migration script ready. Gate to Full Migration.
1.3.M1 | Full Migration Complete | May 8, 2026 | UAT plan ready, data integrity verified. Gate to SIT & KUT.
1.4.M1 | SIT & KUT Complete | May 22, 2026 | System tested, users trained, content signed off. Gate to Final Validation.
1.5.M1 | Phase 1 Complete – Go-Live | Jun 5, 2026 | All defects resolved, delta data migrated, stakeholder sign-off.
2.1.M1 | Project Complete | Jul 3, 2026 | All integration workflows deployed. Full project close-out.

## Slide 6: WES Project Plan — Gantt Chart
Chart: Working Days from Project Start (Apr 13, 2026)
| 2.1.M1 Project Complete — All integration workflows depl... | 2.1.D1 Integration deployed & operational | 2.1.3 Deploy integration as a separate milestone | 2.1.2 Execute integration testing | 2.1.1 Develop integration workflows post go-live | 2.1 Integration | 1.5.M1 Phase 1 Complete — Go-Live, stakeholder sign-off ... | 1.5.D1 Final Project Report & Stakeholder Sign-Off | 1.5.CR2 Review Documentation (if applicable) | 1.5.CR1 Participate in Handover | 1.5.3 Migrate delta data & deploy final content + integr... | 1.5.2 Capture feedback, resolve defects | 1.5.1 Execute UAT with business users | 1.5 Final Validation & Deployment Prep | 1.4.M1 SIT & KUT Complete — UAT-ready, content signed off | 1.4.D2 All transformed content verified and signed off b... | 1.4.D1 UAT-ready system | 1.4.CR3 Review final transformed content and provide sig... | 1.4.CR2 Provide UAT Feedback | 1.4.CR1 Conduct UAT | 1.4.3 Conduct KUT (Key User Training) | 1.4.2 Execute SIT (System Integration Testing) | 1.4.1 Complete content transformation and get sign-off | 1.4 SIT & KUT | 1.3.M1 Full Migration Complete — UAT plan ready, data in... | 1.3.D2 UAT Plan | 1.3.D1 Content transformation progress report | 1.3.CR2 Confirm UAT Scope | 1.3.CR1 Review UAT Migration Results | 1.3.4 Prepare UAT plan and user stories | 1.3.3 Run data integrity checks | 1.3.2 Content Transformation — begin modifying content i... | 1.3.1 Execute migration to UAT environment | 1.3 Full Migration | 1.2.M1 Initial Migration Complete — SSO & migration scri... | 1.2.D2 Initial migration plans | 1.2.D1 SSO integration setup complete | 1.2.3 Validate integration test endpoints | 1.2.2 Develop Initial Migration Script | 1.2.1 Set up SSO Authentication | 1.2 Initial Migration | 1.1.M1 Prep Phase Complete — Project plan finalized, env... | 1.1.CR1 Help in finalizing project goals, expectations, ... | 1.1.CD2 API access and credentials provided | 1.1.CD1 Signed-off project charter | 1.1.5 Set up UAT and Prod environments | 1.1.4 Prepare and finalize project plan | 1.1.3 Receive 3rd-party APIs from Client for integration | 1.1.2 Define key stakeholders and project governance | 1.1.1 Conduct kickoff meeting | 1.1 Prep Phase
Start Offset | 59 | 59 | 57 | 50 | 40 | 40 | 39 | 39 | 38 | 38 | 37 | 33 | 30 | 30 | 29 | 29 | 29 | 25 | 27 | 25 | 27 | 22 | 20 | 20 | 19 | 19 | 19 | 18 | 18 | 16 | 17 | 15 | 15 | 15 | 14 | 14 | 14 | 12 | 10 | 10 | 10 | 9 | 0 | 0 | 7 | 4 | 2 | 0 | 0 | 0 | 0
Duration | 1 | 1 | 3 | 8 | 10 | 20 | 1 | 1 | 2 | 2 | 3 | 5 | 5 | 10 | 1 | 1 | 1 | 5 | 3 | 5 | 3 | 6 | 5 | 10 | 1 | 1 | 1 | 2 | 2 | 4 | 2 | 5 | 3 | 5 | 1 | 1 | 1 | 3 | 4 | 3 | 5 | 1 | 5 | 5 | 3 | 6 | 6 | 5 | 3 | 2 | 10

## Slide 7: WBS Detail — Sprint 0–1: Prep & Initial Migration
WBS # | Type | Task / Deliverable | Owner | Start | End | Days
1.1 | Summary | Prep Phase |  | Apr 13, 2026 | Apr 24, 2026 | 10
1.1.1 | Task | Conduct kickoff meeting | WES / Knowmax | Apr 13, 2026 | Apr 14, 2026 | 2
1.1.2 | Task | Define key stakeholders and project governance | WES / Knowmax | Apr 13, 2026 | Apr 15, 2026 | 3
1.1.3 | Task | Receive 3rd-party APIs from WES for integration | WES | Apr 13, 2026 | Apr 17, 2026 | 5
1.1.4 | Task | Prepare and finalize project plan | Knowmax | Apr 15, 2026 | Apr 22, 2026 | 6
1.1.5 | Task | Set up UAT and Prod environments | Knowmax | Apr 17, 2026 | Apr 24, 2026 | 6
1.1.CD1 | Knowmax Deliverable | Signed-off project charter | Knowmax | Apr 22, 2026 | Apr 24, 2026 | 3
1.1.CD2 | Knowmax Deliverable | API access and credentials provided | WES | Apr 13, 2026 | Apr 17, 2026 | 5
1.1.CR1 | WES Requirement | Help in finalizing project goals, expectations, and scope | WES | Apr 13, 2026 | Apr 17, 2026 | 5
1.1.M1 | ◆ Milestone | Prep Phase Complete, Project plan finalized, environments ready |  | Apr 24, 2026 | Apr 24, 2026 | 1
1.2 | Summary | Initial Migration |  | Apr 27, 2026 | May 1, 2026 | 5
1.2.1 | Task | Set up SSO Authentication | Knowmax | Apr 27, 2026 | Apr 29, 2026 | 3
1.2.2 | Task | Develop Initial Migration Script | Knowmax | Apr 27, 2026 | Apr 30, 2026 | 4
1.2.3 | Task | Validate integration test endpoints | Knowmax | Apr 29, 2026 | May 1, 2026 | 3
1.2.D1 | Deliverable | SSO integration setup complete | Knowmax | May 1, 2026 | May 1, 2026 | 1
1.2.D2 | Deliverable | Initial migration plans | Knowmax | May 1, 2026 | May 1, 2026 | 1
1.2.M1 | ◆ Milestone | Initial Migration Complete, SSO & migration script ready |  | May 1, 2026 | May 1, 2026 | 1

## Slide 8: WBS Detail — Sprint 2–3: Full Migration & SIT/KUT
WBS # | Type | Task / Deliverable | Owner | Start | End | Days
1.3 | Summary | Full Migration |  | May 4, 2026 | May 8, 2026 | 5
1.3.1 | Task | Execute migration to UAT environment | Knowmax | May 4, 2026 | May 6, 2026 | 3
1.3.2 | Task | Content Transformation (begin modifying content in Knowmax) | Knowmax / WES | May 4, 2026 | May 8, 2026 | 5
1.3.3 | Task | Run data integrity checks | Knowmax | May 6, 2026 | May 7, 2026 | 2
1.3.4 | Task | Prepare UAT plan and user stories | Knowmax | May 5, 2026 | May 8, 2026 | 4
1.3.CR1 | WES Requirement | Review UAT Migration Results | WES | May 7, 2026 | May 8, 2026 | 2
1.3.CR2 | WES Requirement | Confirm UAT Scope | WES | May 7, 2026 | May 8, 2026 | 2
1.3.D1 | Deliverable | Content transformation progress report | Knowmax | May 8, 2026 | May 8, 2026 | 1
1.3.D2 | Deliverable | UAT Plan | Knowmax | May 8, 2026 | May 8, 2026 | 1
1.3.A1 | Assumption | Content Transformation Team starts Day 1 of this sprint (if required) |  |  |  | 
1.3.R1 | Risk | Commercials may change based on Scope Finalization |  |  |  | 
1.3.M1 | ◆ Milestone | Full Migration Complete — UAT plan ready, data integrity verified |  | May 8, 2026 | May 8, 2026 | 1
1.4 | Summary | SIT & KUT |  | May 11, 2026 | May 22, 2026 | 10
1.4.1 | Task | Complete content transformation and get sign-off | Knowmax / WES | May 11, 2026 | May 15, 2026 | 5
1.4.2 | Task | Execute SIT (System Integration Testing) | Knowmax | May 13, 2026 | May 20, 2026 | 6
1.4.3 | Task | Conduct KUT (Key User Training) | Knowmax / WES | May 20, 2026 | May 22, 2026 | 3
1.4.CR1 | WES Requirement | Conduct UAT | WES | May 18, 2026 | May 22, 2026 | 5
1.4.CR2 | WES Requirement | Provide UAT Feedback | WES | May 20, 2026 | May 22, 2026 | 3
1.4.CR3 | WES Requirement | Review final transformed content and provide sign-off | WES | May 18, 2026 | May 22, 2026 | 5
1.4.D1 | Deliverable | UAT-ready system | Knowmax | May 22, 2026 | May 22, 2026 | 1
1.4.D2 | Deliverable | All transformed content verified and signed off by client | WES | May 22, 2026 | May 22, 2026 | 1
1.4.M1 | ◆ Milestone | SIT & KUT Complete — UAT-ready, content signed off |  | May 22, 2026 | May 22, 2026 | 1

## Slide 9: WBS Detail — Sprint 4–5: Final Validation & Phase 2
WBS # | Type | Task / Deliverable | Owner | Start | End | Days
1.5 | Summary | Final Validation & Deployment Prep |  | May 25, 2026 | Jun 5, 2026 | 10
1.5.1 | Task | Execute UAT with business users | Knowmax / WES | May 25, 2026 | May 29, 2026 | 5
1.5.2 | Task | Capture feedback, resolve defects | Knowmax | May 28, 2026 | Jun 3, 2026 | 5
1.5.3 | Task | Migrate delta data & deploy final content + integration | Knowmax | Jun 3, 2026 | Jun 5, 2026 | 3
1.5.CR1 | WES Requirement | Participate in Handover | WES | Jun 4, 2026 | Jun 5, 2026 | 2
1.5.CR2 | WES Requirement | Review Documentation (if applicable) | WES | Jun 4, 2026 | Jun 5, 2026 | 2
1.5.D1 | Deliverable | Final Project Report & Stakeholder Sign-Off | Knowmax / WES | Jun 5, 2026 | Jun 5, 2026 | 1
1.5.R1 | Risk | Commercials may change based on Scope Finalization |  |  |  | 
1.5.M1 | ◆ Milestone | Phase 1 Complete : Go-Live, stakeholder sign-off received |  | Jun 5, 2026 | Jun 5, 2026 | 1
2.1 | Summary | Integration |  | Jun 8, 2026 | Jul 3, 2026 | 20
2.1.1 | Task | Develop integration workflows post go-live | Knowmax | Jun 8, 2026 | Jun 19, 2026 | 10
2.1.2 | Task | Execute integration testing | Knowmax | Jun 22, 2026 | Jul 1, 2026 | 8
2.1.3 | Task | Deploy integration as a separate milestone | Knowmax | Jul 1, 2026 | Jul 3, 2026 | 3
2.1.D1 | Deliverable | Integration deployed & operational | Knowmax / WES | Jul 3, 2026 | Jul 3, 2026 | 1
2.1.A1 | Assumption | Integration timeline is subject to change after requirement finalization |  |  |  | 
2.1.R1 | Risk | Commercials may change based on Scope Finalization |  |  |  | 
2.1.M1 | ◆ Milestone | Project Complete : Integration workflows deployed |  | Jul 3, 2026 | Jul 3, 2026 | 1

## Slide 10: How to Use & Important Notes
How to Use the WBS
Track progress — Update Status dropdown (col J). Green=Done, yellow=In Progress, red=Blocked.
Check dependencies — Verify dependencies (col K) are Completed before starting any task.
Monitor WES items — Filter by WES Requirement to track what WES needs to provide. Delays cascade to Knowmax.
Monitor Knowmax deliverables — Filter by Knowmax Deliverable to track artifacts owed. Late deliverables block WES actions.
Watch risks & assumptions — Purple/orange rows flagged for attention. Escalate if they materialize.
⚠ Important Notes
Commercials may change based on scope finalization.
Content Transformation is optional and should start from Day 1 of Sprint 2 (if required).
Integration timeline (Phase 2) subject to change after requirement finalization.
All dates use working days only (Mon–Fri).
⚠ DISCLAIMER
This timeline is tentative and subject to change. Actual dates may be preponed or postponed based on:
Scope changes or requirement finalization delays
Availability of third-party APIs, credentials, or environment access from WES
Volume and complexity of content transformation work
Defect resolution timelines during SIT/UAT phases
Resource availability on either WES or Knowmax side
Dependencies on external integrations or third-party systems. Commercials may also change based on final scope finalization.

## Slide 11: Status Legend
Not Started
Work has not yet begun
In Progress
Work is actively underway
Completed
Work is finished and verified
On Hold
Paused, awaiting decision or input
Blocked
Cannot proceed — escalate immediately