## WBS Guide (hidden)
WES Project Plan — Work Breakdown Structure (WBS) Guide
1. OVERVIEW
This WBS breaks down the WES Project Plan into a structured, trackable format across 2 phases, 6 sprints, and 60 working days (Apr 13 – Jul 3, 2026). Every task, deliverable, client obligation, milestone, risk, and assumption from the source project plan is captured in the WBS sheet.
2. HOW TO READ THE WBS
The WBS sheet contains 12 columns described below:
Column | Purpose
WBS # (A) | Hierarchical numbering — 1.x = Phase 1, 2.x = Phase 2. Sub-levels denote sprint (.1, .2) and task (.1.1, .1.2). Suffixes: CD = Client Deliverable, CR = Client Requirement, D = Deliverable, M = Milestone, A = Assumption, R = Risk.
Phase (B) | Which project phase the item belongs to (Phase 1: Migration & Integration, or Phase 2: Integration Post Go-Live).
Sprint (C) | Sprint grouping with corresponding week range (e.g., Sprint 0 Wk 0–2, Sprint 1 Wk 3, etc.).
Type (D) | Classification of the row — Task, Summary, Milestone, Client Deliverable, Deliverable, Client Requirement, Assumption, or Risk. See Section 3 for color coding.
Task / Deliverable (E) | Description of the work item, output, or obligation.
Owner (F) | Who is responsible — WES, Client, or WES / Client (joint responsibility).
Start / End Date (G–H) | Working-day calendar dates (Monday–Friday only). Weekends are excluded from all scheduling.
Duration (I) | Auto-calculated using NETWORKDAYS() formula — counts only working days (excludes Sat/Sun).
Status (J) | Dropdown with options: Not Started, In Progress, Completed, On Hold, Blocked. Conditional formatting auto-highlights by color.
Dependencies (K) | WBS # of items that must complete before this item can start. Check these before beginning work.
Notes (L) | Assumptions, conditions, caveats, or additional context from the project plan.
3. ROW TYPES & COLOR CODING
Each row in the WBS is classified by Type (column D). The color coding makes it easy to scan and identify item categories at a glance:
Type | Color | What It Means
Summary | ■ | Sprint-level summary row. Shows the sprint’s total date range and working-day duration. This is a container row, not an executable work item.
Task | ■ | Actual work to be performed by WES, Client, or both. These are the executable activities that move the project forward.
◆ Milestone | ◆ | A checkpoint or gate with zero duration. Marks that all preceding items in the sprint are complete. Used as go/no-go gates before the next sprint. If a milestone is not met, the project should not proceed.
Knowmax Deliverable | ■ | Something KNOWMAX must provide to WES (e.g., signed charter, SSO setup, UAT plan). These are tangible artifacts. If late, downstream tasks will be blocked.
Deliverable | ■ | An output WES produces (e.g., SSO setup, UAT plan, migration report). These are tangible project artifacts delivered by the WES team.
WES Requirement | ■ | An ACTION that WES must take (e.g., conduct UAT, provide feedback, review content, provide APIs). These are activities, not artifacts. Delays here cascade to Knowmax timelines.
Assumption | ■ | A stated assumption the plan depends on. If this assumption changes, timelines and commercials may shift. Track and validate early.
Risk | ■ | An identified risk to the project (e.g., scope changes affecting commercials). Monitor throughout the project and escalate if they materialize.
4. SPRINT TIMELINE
Sprint | Weeks | Dates | Working Days | Focus
Sprint 0 | Wk 0–2 | Apr 13 – Apr 24 | 10 | Prep: kickoff, governance, APIs, environments
Sprint 1 | Wk 3 | Apr 27 – May 1 | 5 | Initial Migration: SSO, migration script, endpoint validation
Sprint 2 | Wk 4 | May 4 – May 8 | 5 | Full Migration: UAT migration, content transformation, data integrity
Sprint 3 | Wk 5–6 | May 11 – May 22 | 10 | SIT & KUT: system integration testing, key user training, UAT
Sprint 4 | Wk 7–8 | May 25 – Jun 5 | 10 | Final Validation: UAT with users, defect resolution, go-live deployment
Sprint 5 (Phase 2) | Wk 9–12 | Jun 8 – Jul 3 | 20 | Integration: post go-live workflows, integration testing, deployment
5. KEY MILESTONES (6 Total)
WBS # | Milestone | Date | Significance
1.1.M1 | Prep Phase Complete | 2026-04-24 | Project plan finalized, UAT & Prod environments ready. Gate to Sprint 1.
1.2.M1 | Initial Migration Complete | 2026-05-01 | SSO set up, migration script ready, endpoints validated. Gate to Full Migration.
1.3.M1 | Full Migration Complete | 2026-05-08 | UAT plan ready, data integrity verified. Gate to SIT & KUT.
1.4.M1 | SIT & KUT Complete | 2026-05-22 | System tested, users trained, UAT-ready, content signed off. Gate to Final Validation.
1.5.M1 | ⭐ Phase 1 Complete — Go-Live | 2026-06-05 | MAJOR: All defects resolved, delta data migrated, final content deployed, stakeholder sign-off received.
2.1.M1 | ⭐ Project Complete | 2026-07-03 | MAJOR: All integration workflows developed, tested, and deployed. Full project close-out.
6. HOW TO USE THIS WBS
# | Action | How
1 | Track progress | Update the Status dropdown in column J as work progresses. Conditional formatting auto-highlights: green = Completed, yellow = In Progress, red = Blocked, orange = On Hold.
2 | Check dependencies | Before starting any task, verify its dependencies (column K) are marked as Completed. Starting work with unfinished dependencies risks rework.
3 | Monitor client items | Filter column D (Type) by "Client Deliverable" or "Client Requirement" to see what is needed from the client and by when. Late client items will cascade delays to WES tasks.
4 | Use the Gantt chart | The "Gantt Chart" tab provides a visual timeline of all tasks. Bars are color-coded to match the row types described in Section 3 above.
5 | Watch risks & assumptions | Risk and Assumption rows (purple/orange) are flagged for ongoing attention. If scope changes, update commercials and timeline accordingly.
7. IMPORTANT NOTES FROM SOURCE PLAN
⚠ | Commercials may change based on scope finalization.
⚠ | Content Transformation is optional and starts Day 1 of Sprint 2 (if required).
⚠ | Integration timeline (Phase 2) is subject to change after requirement finalization.
⚠ | All dates use working days only (Monday–Friday). Weekends are excluded from all scheduling and duration calculations.
TIMELINE DISCLAIMER
This timeline is tentative and subject to change. Actual dates may be preponed or postponed based on: (1) Scope changes or requirement finalization delays; (2) Availability of third-party APIs, credentials, or environment access from WES; (3) Volume and complexity of content transformation work; (4) Defect resolution timelines during SIT/UAT phases; (5) Resource availability on either WES or Knowmax side; (6) Dependencies on external integrations or third-party systems. Commercials may also change based on final scope finalization. All stakeholders will be notified promptly of any schedule adjustments.
Status | Color | Meaning
8. STATUS LEGEND | ■ Default (no highlight) | Work has not yet begun on this item.
In Progress | ■ Yellow | Work is actively underway.
Completed | ■ Green | Work is finished and verified.
On Hold | ■ Orange | Work is paused, awaiting a decision or external input.
Blocked | ■ Red | Work cannot proceed due to an unresolved dependency or issue. Escalate immediately.

## WBS
WBS # | Phase | Sprint | Type | Task / Deliverable | Owner | Start Date | End Date | Duration (Working Days) | Status | Dependencies | Notes
1 | Phase 1: Migration & Integration
1.1 | Phase 1 | Sprint 0 (Wk 0–2) | Summary | Prep Phase |  | 2026-04-13 | 2026-04-24 | 10 |  | —
1.1.1 | Phase 1 | Sprint 0 | Task | Conduct kickoff meeting | WES / Knowmax | 2026-04-13 | 2026-04-14 | 2 | Not Started | —
1.1.2 | Phase 1 | Sprint 0 | Task | Define key stakeholders and project governance | WES / Knowmax | 2026-04-13 | 2026-04-15 | 3 | Not Started | —
1.1.3 | Phase 1 | Sprint 0 | Task | Receive 3rd-party APIs from WES for integration | WES | 2026-04-13 | 2026-04-17 | 5 | Not Started | — | WES dependency
1.1.4 | Phase 1 | Sprint 0 | Task | Prepare and finalize project plan | Knowmax | 2026-04-15 | 2026-04-22 | 6 | Not Started | 1.1.1, 1.1.2
1.1.5 | Phase 1 | Sprint 0 | Task | Set up UAT and Prod environments | Knowmax | 2026-04-17 | 2026-04-24 | 6 | Not Started | 1.1.3
1.1.CD1 | Phase 1 | Sprint 0 | Knowmax Deliverable | Signed-off project charter | Knowmax | 2026-04-22 | 2026-04-24 | 3 | Not Started | 1.1.4 | Knowmax to finalize, WES to review & sign off
1.1.CD2 | Phase 1 | Sprint 0 | Knowmax Deliverable | API access and credentials provided | WES | 2026-04-13 | 2026-04-17 | 5 | Not Started | — | Required for integration setup
1.1.CR1 | Phase 1 | Sprint 0 | WES Requirement | Help in finalizing project goals, expectations, and scope | WES | 2026-04-13 | 2026-04-17 | 5 | Not Started | —
1.1.M1 | Phase 1 | Sprint 0 | ◆ Milestone | Prep Phase Complete — Project plan finalized, environments ready |  | 2026-04-24 | 2026-04-24 | 1 | Not Started | 1.1.5, 1.1.CD1 | Gate: proceed to Sprint 1
1.2 | Phase 1 | Sprint 1 (Wk 3) | Summary | Initial Migration |  | 2026-04-27 | 2026-05-01 | 5 |  | 1.1
1.2.1 | Phase 1 | Sprint 1 | Task | Set up SSO Authentication | Knowmax | 2026-04-27 | 2026-04-29 | 3 | Not Started | 1.1.CD2
1.2.2 | Phase 1 | Sprint 1 | Task | Develop Initial Migration Script | Knowmax | 2026-04-27 | 2026-04-30 | 4 | Not Started | 1.1.5
1.2.3 | Phase 1 | Sprint 1 | Task | Validate integration test endpoints | Knowmax | 2026-04-29 | 2026-05-01 | 3 | Not Started | 1.2.1 | If there are any
1.2.D1 | Phase 1 | Sprint 1 | Deliverable | SSO integration setup complete | Knowmax | 2026-05-01 | 2026-05-01 | 1 | Not Started | 1.2.1
1.2.D2 | Phase 1 | Sprint 1 | Deliverable | Initial migration plans | Knowmax | 2026-05-01 | 2026-05-01 | 1 | Not Started | 1.2.2
1.2.M1 | Phase 1 | Sprint 1 | ◆ Milestone | Initial Migration Complete — SSO & migration script ready |  | 2026-05-01 | 2026-05-01 | 1 | Not Started | 1.2.3, 1.2.D1, 1.2.D2 | Gate: proceed to Full Migration
1.3 | Phase 1 | Sprint 2 (Wk 4) | Summary | Full Migration |  | 2026-05-04 | 2026-05-08 | 5 |  | 1.2
1.3.1 | Phase 1 | Sprint 2 | Task | Execute migration to UAT environment | Knowmax | 2026-05-04 | 2026-05-06 | 3 | Not Started | 1.2.2
1.3.2 | Phase 1 | Sprint 2 | Task | Content Transformation — begin modifying content in Knowmax | Knowmax / WES | 2026-05-04 | 2026-05-08 | 5 | Not Started | — | Optional — if required
1.3.3 | Phase 1 | Sprint 2 | Task | Run data integrity checks | Knowmax | 2026-05-06 | 2026-05-07 | 2 | Not Started | 1.3.1
1.3.4 | Phase 1 | Sprint 2 | Task | Prepare UAT plan and user stories | Knowmax | 2026-05-05 | 2026-05-08 | 4 | Not Started | 1.3.1
1.3.CR1 | Phase 1 | Sprint 2 | WES Requirement | Review UAT Migration Results | WES | 2026-05-07 | 2026-05-08 | 2 | Not Started | 1.3.1
1.3.CR2 | Phase 1 | Sprint 2 | WES Requirement | Confirm UAT Scope | WES | 2026-05-07 | 2026-05-08 | 2 | Not Started | 1.3.4
1.3.D1 | Phase 1 | Sprint 2 | Deliverable | Content transformation progress report | Knowmax | 2026-05-08 | 2026-05-08 | 1 | Not Started | 1.3.2
1.3.D2 | Phase 1 | Sprint 2 | Deliverable | UAT Plan | Knowmax | 2026-05-08 | 2026-05-08 | 1 | Not Started | 1.3.4
1.3.A1 | Phase 1 | Sprint 2 | Assumption | Content Transformation Team starts Day 1 of this sprint (if required)
1.3.R1 | Phase 1 | Sprint 2 | Risk | Commercials may change based on Scope Finalization
1.3.M1 | Phase 1 | Sprint 2 | ◆ Milestone | Full Migration Complete — UAT plan ready, data integrity verified |  | 2026-05-08 | 2026-05-08 | 1 | Not Started | 1.3.3, 1.3.D2, 1.3.CR2 | Gate: proceed to SIT & KUT
1.4 | Phase 1 | Sprint 3 (Wk 5–6) | Summary | SIT & KUT |  | 2026-05-11 | 2026-05-22 | 10 |  | 1.3
1.4.1 | Phase 1 | Sprint 3 | Task | Complete content transformation and get sign-off | Knowmax / WES | 2026-05-11 | 2026-05-15 | 5 | Not Started | 1.3.2
1.4.2 | Phase 1 | Sprint 3 | Task | Execute SIT (System Integration Testing) | Knowmax | 2026-05-13 | 2026-05-20 | 6 | Not Started | 1.4.1, 1.3.1
1.4.3 | Phase 1 | Sprint 3 | Task | Conduct KUT (Key User Training) | Knowmax / WES | 2026-05-20 | 2026-05-22 | 3 | Not Started | 1.4.2
1.4.CR1 | Phase 1 | Sprint 3 | WES Requirement | Conduct UAT | WES | 2026-05-18 | 2026-05-22 | 5 | Not Started | 1.4.2
1.4.CR2 | Phase 1 | Sprint 3 | WES Requirement | Provide UAT Feedback | WES | 2026-05-20 | 2026-05-22 | 3 | Not Started | 1.4.CR1
1.4.CR3 | Phase 1 | Sprint 3 | WES Requirement | Review final transformed content and provide sign-off | WES | 2026-05-18 | 2026-05-22 | 5 | Not Started | 1.4.1 | Team will review the transformed content
1.4.D1 | Phase 1 | Sprint 3 | Deliverable | UAT-ready system | Knowmax | 2026-05-22 | 2026-05-22 | 1 | Not Started | 1.4.2, 1.4.3
1.4.D2 | Phase 1 | Sprint 3 | Deliverable | All transformed content verified and signed off by client | WES | 2026-05-22 | 2026-05-22 | 1 | Not Started | 1.4.CR3
1.4.M1 | Phase 1 | Sprint 3 | ◆ Milestone | SIT & KUT Complete — UAT-ready, content signed off |  | 2026-05-22 | 2026-05-22 | 1 | Not Started | 1.4.D1, 1.4.D2 | Gate: proceed to Final Validation
1.5 | Phase 1 | Sprint 4 (Wk 7–8) | Summary | Final Validation & Deployment Prep |  | 2026-05-25 | 2026-06-05 | 10 |  | 1.4
1.5.1 | Phase 1 | Sprint 4 | Task | Execute UAT with business users | Knowmax / WES | 2026-05-25 | 2026-05-29 | 5 | Not Started | 1.4.D1
1.5.2 | Phase 1 | Sprint 4 | Task | Capture feedback, resolve defects | Knowmax | 2026-05-28 | 2026-06-03 | 5 | Not Started | 1.5.1
1.5.3 | Phase 1 | Sprint 4 | Task | Migrate delta data & deploy final content + integration | Knowmax | 2026-06-03 | 2026-06-05 | 3 | Not Started | 1.5.2
1.5.CR1 | Phase 1 | Sprint 4 | WES Requirement | Participate in Handover | WES | 2026-06-04 | 2026-06-05 | 2 | Not Started | 1.5.3
1.5.CR2 | Phase 1 | Sprint 4 | WES Requirement | Review Documentation (if applicable) | WES | 2026-06-04 | 2026-06-05 | 2 | Not Started | 1.5.3 | If there are any
1.5.D1 | Phase 1 | Sprint 4 | Deliverable | Final Project Report & Stakeholder Sign-Off | Knowmax / WES | 2026-06-05 | 2026-06-05 | 1 | Not Started | 1.5.3, 1.5.CR1
1.5.R1 | Phase 1 | Sprint 4 | Risk | Commercials may change based on Scope Finalization
1.5.M1 | Phase 1 | Sprint 4 | ◆ Milestone | Phase 1 Complete — Go-Live, stakeholder sign-off received |  | 2026-06-05 | 2026-06-05 | 1 | Not Started | 1.5.D1 | MAJOR: Phase 1 close-out
2 | Phase 2: Integration (Post Go-Live)
2.1 | Phase 2 | Sprint 5 (Wk 9–12) | Summary | Integration |  | 2026-06-08 | 2026-07-03 | 20 |  | 1.5 | Timeline subject to change after requirement finalization
2.1.1 | Phase 2 | Sprint 5 | Task | Develop integration workflows post go-live | Knowmax | 2026-06-08 | 2026-06-19 | 10 | Not Started | 1.5.M1
2.1.2 | Phase 2 | Sprint 5 | Task | Execute integration testing | Knowmax | 2026-06-22 | 2026-07-01 | 8 | Not Started | 2.1.1
2.1.3 | Phase 2 | Sprint 5 | Task | Deploy integration as a separate milestone | Knowmax | 2026-07-01 | 2026-07-03 | 3 | Not Started | 2.1.2
2.1.D1 | Phase 2 | Sprint 5 | Deliverable | Integration deployed & operational | Knowmax / WES | 2026-07-03 | 2026-07-03 | 1 | Not Started | 2.1.3
2.1.A1 | Phase 2 | Sprint 5 | Assumption | Integration timeline is subject to change after requirement finalization
2.1.R1 | Phase 2 | Sprint 5 | Risk | Commercials may change based on Scope Finalization
2.1.M1 | Phase 2 | Sprint 5 | ◆ Milestone | Project Complete — All integration workflows deployed |  | 2026-07-03 | 2026-07-03 | 1 | Not Started | 2.1.D1 | MAJOR: Project close-out
⚠ DISCLAIMER: This timeline is tentative and subject to change. Actual dates may be preponed or postponed based on: (1) Scope changes or requirement finalization delays; (2) Availability of third-party APIs, credentials, or environment access from WES; (3) Volume and complexity of content transformation work; (4) Defect resolution timelines during SIT/UAT phases; (5) Resource availability on either WES or Knowmax side; (6) Dependencies on external integrations or third-party systems. Commercials may also change based on final scope finalization. All stakeholders will be notified promptly of any schedule adjustments.
Formulas:
Duration (Working Days) = NETWORKDAYS([Start Date],[End Date])

## Gantt Chart (hidden)
Task | Type | Start Offset (Days) | Duration (Days) | Phase | Task | Start Offset | Duration
2.1.M1 Project Complete — All integration workflows depl... | ◆ Milestone | 81 | 1 | Phase 2 | 2.1.M1 Project Complete — All integration workflows depl... | 81 | 1
2.1.D1 Integration deployed & operational | Deliverable | 81 | 1 | Phase 2 | 2.1.D1 Integration deployed & operational | 81 | 1
2.1.3 Deploy integration as a separate milestone | Task | 79 | 2 | Phase 2 | 2.1.3 Deploy integration as a separate milestone | 79 | 2
2.1.2 Execute integration testing | Task | 70 | 9 | Phase 2 | 2.1.2 Execute integration testing | 70 | 9
2.1.1 Develop integration workflows post go-live | Task | 56 | 11 | Phase 2 | 2.1.1 Develop integration workflows post go-live | 56 | 11
2.1 Integration | Summary | 56 | 25 | Phase 2 | 2.1 Integration | 56 | 25
1.5.M1 Phase 1 Complete — Go-Live, stakeholder sign-off ... | ◆ Milestone | 53 | 1 | Phase 1 | 1.5.M1 Phase 1 Complete — Go-Live, stakeholder sign-off ... | 53 | 1
1.5.D1 Final Project Report & Stakeholder Sign-Off | Deliverable | 53 | 1 | Phase 1 | 1.5.D1 Final Project Report & Stakeholder Sign-Off | 53 | 1
1.5.CR2 Review Documentation (if applicable) | Client Requirement | 52 | 1 | Phase 1 | 1.5.CR2 Review Documentation (if applicable) | 52 | 1
1.5.CR1 Participate in Handover | Client Requirement | 52 | 1 | Phase 1 | 1.5.CR1 Participate in Handover | 52 | 1
1.5.3 Migrate delta data & deploy final content + integr... | Task | 51 | 2 | Phase 1 | 1.5.3 Migrate delta data & deploy final content + integr... | 51 | 2
1.5.2 Capture feedback, resolve defects | Task | 45 | 6 | Phase 1 | 1.5.2 Capture feedback, resolve defects | 45 | 6
1.5.1 Execute UAT with business users | Task | 42 | 4 | Phase 1 | 1.5.1 Execute UAT with business users | 42 | 4
1.5 Final Validation & Deployment Prep | Summary | 42 | 11 | Phase 1 | 1.5 Final Validation & Deployment Prep | 42 | 11
1.4.M1 SIT & KUT Complete — UAT-ready, content signed off | ◆ Milestone | 39 | 1 | Phase 1 | 1.4.M1 SIT & KUT Complete — UAT-ready, content signed off | 39 | 1
1.4.D2 All transformed content verified and signed off b... | Deliverable | 39 | 1 | Phase 1 | 1.4.D2 All transformed content verified and signed off b... | 39 | 1
1.4.D1 UAT-ready system | Deliverable | 39 | 1 | Phase 1 | 1.4.D1 UAT-ready system | 39 | 1
1.4.CR3 Review final transformed content and provide sig... | Client Requirement | 35 | 4 | Phase 1 | 1.4.CR3 Review final transformed content and provide sig... | 35 | 4
1.4.CR2 Provide UAT Feedback | Client Requirement | 37 | 2 | Phase 1 | 1.4.CR2 Provide UAT Feedback | 37 | 2
1.4.CR1 Conduct UAT | Client Requirement | 35 | 4 | Phase 1 | 1.4.CR1 Conduct UAT | 35 | 4
1.4.3 Conduct KUT (Key User Training) | Task | 37 | 2 | Phase 1 | 1.4.3 Conduct KUT (Key User Training) | 37 | 2
1.4.2 Execute SIT (System Integration Testing) | Task | 30 | 7 | Phase 1 | 1.4.2 Execute SIT (System Integration Testing) | 30 | 7
1.4.1 Complete content transformation and get sign-off | Task | 28 | 4 | Phase 1 | 1.4.1 Complete content transformation and get sign-off | 28 | 4
1.4 SIT & KUT | Summary | 28 | 11 | Phase 1 | 1.4 SIT & KUT | 28 | 11
1.3.M1 Full Migration Complete — UAT plan ready, data in... | ◆ Milestone | 25 | 1 | Phase 1 | 1.3.M1 Full Migration Complete — UAT plan ready, data in... | 25 | 1
1.3.D2 UAT Plan | Deliverable | 25 | 1 | Phase 1 | 1.3.D2 UAT Plan | 25 | 1
1.3.D1 Content transformation progress report | Deliverable | 25 | 1 | Phase 1 | 1.3.D1 Content transformation progress report | 25 | 1
1.3.CR2 Confirm UAT Scope | Client Requirement | 24 | 1 | Phase 1 | 1.3.CR2 Confirm UAT Scope | 24 | 1
1.3.CR1 Review UAT Migration Results | Client Requirement | 24 | 1 | Phase 1 | 1.3.CR1 Review UAT Migration Results | 24 | 1
1.3.4 Prepare UAT plan and user stories | Task | 22 | 3 | Phase 1 | 1.3.4 Prepare UAT plan and user stories | 22 | 3
1.3.3 Run data integrity checks | Task | 23 | 1 | Phase 1 | 1.3.3 Run data integrity checks | 23 | 1
1.3.2 Content Transformation — begin modifying content i... | Task | 21 | 4 | Phase 1 | 1.3.2 Content Transformation — begin modifying content i... | 21 | 4
1.3.1 Execute migration to UAT environment | Task | 21 | 2 | Phase 1 | 1.3.1 Execute migration to UAT environment | 21 | 2
1.3 Full Migration | Summary | 21 | 4 | Phase 1 | 1.3 Full Migration | 21 | 4
1.2.M1 Initial Migration Complete — SSO & migration scri... | ◆ Milestone | 18 | 1 | Phase 1 | 1.2.M1 Initial Migration Complete — SSO & migration scri... | 18 | 1
1.2.D2 Initial migration plans | Deliverable | 18 | 1 | Phase 1 | 1.2.D2 Initial migration plans | 18 | 1
1.2.D1 SSO integration setup complete | Deliverable | 18 | 1 | Phase 1 | 1.2.D1 SSO integration setup complete | 18 | 1
1.2.3 Validate integration test endpoints | Task | 16 | 2 | Phase 1 | 1.2.3 Validate integration test endpoints | 16 | 2
1.2.2 Develop Initial Migration Script | Task | 14 | 3 | Phase 1 | 1.2.2 Develop Initial Migration Script | 14 | 3
1.2.1 Set up SSO Authentication | Task | 14 | 2 | Phase 1 | 1.2.1 Set up SSO Authentication | 14 | 2
1.2 Initial Migration | Summary | 14 | 4 | Phase 1 | 1.2 Initial Migration | 14 | 4
1.1.M1 Prep Phase Complete — Project plan finalized, env... | ◆ Milestone | 11 | 1 | Phase 1 | 1.1.M1 Prep Phase Complete — Project plan finalized, env... | 11 | 1
1.1.CR1 Help in finalizing project goals, expectations, ... | Client Requirement | 0 | 4 | Phase 1 | 1.1.CR1 Help in finalizing project goals, expectations, ... | 0 | 4
1.1.CD2 API access and credentials provided | Client Deliverable | 0 | 4 | Phase 1 | 1.1.CD2 API access and credentials provided | 0 | 4
1.1.CD1 Signed-off project charter | Client Deliverable | 9 | 2 | Phase 1 | 1.1.CD1 Signed-off project charter | 9 | 2
1.1.5 Set up UAT and Prod environments | Task | 4 | 7 | Phase 1 | 1.1.5 Set up UAT and Prod environments | 4 | 7
1.1.4 Prepare and finalize project plan | Task | 2 | 7 | Phase 1 | 1.1.4 Prepare and finalize project plan | 2 | 7
1.1.3 Receive 3rd-party APIs from Client for integration | Task | 0 | 4 | Phase 1 | 1.1.3 Receive 3rd-party APIs from Client for integration | 0 | 4
1.1.2 Define key stakeholders and project governance | Task | 0 | 2 | Phase 1 | 1.1.2 Define key stakeholders and project governance | 0 | 2
1.1.1 Conduct kickoff meeting | Task | 0 | 1 | Phase 1 | 1.1.1 Conduct kickoff meeting | 0 | 1
1.1 Prep Phase | Summary | 0 | 11 | Phase 1 | 1.1 Prep Phase | 0 | 11
Legend:
■ | Sprint Summary
■ | Task
■ | ◆ Milestone
■ | Client Deliverable
■ | Client Requirement
■ | Deliverable (WES)